## Employees
Employee ID | Name
348642 | Thirumala
348649 | Sibi
349661 | Dinesh
349722 | Abhinash
350050 | Vishnu

## 348642
# | Date | Completed Today | Blockers
1 | 29-09-2026 | Task - 2602: Had a meeting with the team to finalize the device document re-upload feature. Prepared a document on the discussions held about the workflow. | -
2 | 30-09-2026 | Task - 2602: 1. Implemented order-level device document handling by storing the latest available document references in the order_documents JSONB field during order placement. 2. Updated device document retrieval for Desktop DB integration, including MinIO path mapping and handling document re-upload updates. | -
3 | 01-10-2026 | 1. Worked on the Integration service to store the updated device documents during order placement. 2. Started working on updating documents when uploaded on the device details page. | -
4 | 05-10-2026 | 1. Created a controller for fetching order details when a document is updated. 2. Fetched the updated document and replaced it in the orders table. | -
5 | 06-10-2026 | Working on preparing a presentation on Git & GitLab. | -
6 | 07-10-2026 | Presented a Presentation for new joiners on Git & GitLab. | -
7 | 08-10-2026 | Task - 2602 : 1. Implemented and debugged the Update Device Documents gRPC integration. 2. Fixed the gRPC handler export/registration issue causing UNIMPLEMENTED errors. 3. Reviewed and optimized device document retrieval and order document snapshot logic. | -
8 | 09-10-2026 | 1. Updated the ongoing order document retrieval logic to select only the most recent order with ASSIGNED or IN_PROGRESS test assignments. 2. Refined transaction management, error handling, and database connection cleanup for reliable document updates. 3. Researched on Test Reports to prepare a Reports Template. | -

## 348649
# | Date | Completed Today | Blockers
1 | 29-09-2026 | 1. Password Reset Functionality – Worked on the implementation approach for password reset functionality for Client, Admin, and Tester user roles – Ongoing 2. Password Reset Architecture Mapping – Mapped the required architecture and implementation flow for handling password reset securely across the respective user roles – Ongoing | -
2 | 30-09-2026 | 1. Change Password Backend API – Implemented the Change Password functionality for authenticated Client, Admin, and Tester users – Completed 2. Implemented password validation, including current password verification, new password policy validation, confirm-password matching, and password reuse prevention – Completed 3. Implemented secure password updates using bcrypt – Completed 4. Implemented session revocation using revoked_at after a successful password change – Completed 5. Updated the authentication middleware to reject revoked sessions – Completed 6. Implemented the security flow to ensure the old authentication token is rejected after a password change – Completed | -
3 | 01-10-2026 | 1. Completed functional, negative, and security validation for the Change Password functionality across Client, Admin, and Tester user roles – Completed & Verified 2. Validated incorrect current password, password mismatch, invalid password format, password reuse, old token rejection, old password rejection, and login with the new password – Completed & Tested | -
4 | 06-10-2026 | 1. Pushed the completed Change Password code changes to the Server – Completed 2. Completed the Change Password implementation and security testing documentation – Completed | The code has been pushed to the Server. The Frontend implementation is pending and needs to be completed by @Kurni Thirumala.
5 | 07-10-2026 | 1. API to Upload Generated Report Files to MinIO – Reviewed the API implementation, storage path configuration, environment-specific handling, authentication, authorization, file validation, and MinIO integration – Ongoing | -
6 | 08-10-2026 | 1. API to Upload Generated Report Files to MinIO – Continued the review of the API implementation, including authentication, authorization, file validation, MinIO integration, storage configuration, and security considerations – Ongoing 2. PM2 Server Issues – Identified and fixed the PM2-related issues on the server and verified the application services are running correctly – Completed & Verified | -
7 | 09-10-2026 | 1. API to Upload Generated Report Files to MinIO – Completed the API review and started implementing the required functionality, including file validation, authentication, authorization, and MinIO integration – Implementation Ongoing | -

## 349661
# | Date | Completed Today | Blockers
1 | 30-09-2026 | 1. Completed the document upload functionality during Client Device Registration, including the required document handling workflow. 2. Completed the frontend implementation of the Device Details page based on the new document upload architecture. 3. Currently working on the Raise Ticket workflow within the Device Details module, including the required functionality and integration with the new architecture. | NA
2 | 01-10-2026 | 1. Currently working on the Raise Ticket workflow within the Device Details module, focusing on implementing the required functionality in alignment with the new architecture. 2. Initiated backend development for the Raise Ticket workflow, including the implementation of the necessary APIs and supporting logic. | NA
3 | 05-10-2026 | 1. Currently working on the Raise Ticket workflow within the Device Details module, focusing on integrating the required functionality with the new architecture. 2. Completed the backend development for the Raise Ticket workflow, including the required APIs, business logic, and supporting functionality. | N/A
4 | 06-10-2026 | 1. Modified the ticket data persistence flow in the `support_tickets` and `device_document_mapping` tables to align with the updated architecture. 2. Completed the end-to-end Raise Ticket workflow for Device Registration, covering the required frontend and backend functionality. 3. Completed the backend development for the Raise Ticket workflow, including the required APIs, business logic, and supporting functionality. | N/A
5 | 07-10-2026 | 1. Completed the Device Details page and deployed the latest changes to the development environment for further testing and validation. 2. Conducted a presentation for freshers on the Project Management Tool, covering how to access the tool, navigate the relevant sections, view project activities, and update task status and other required details. | -
6 | 08-10-2026 | 1. Started implementing the Client Device Registration document upload workflow, with documents being stored directly in MinIO. 2. Completed the Device Details page and deployed the latest changes to the development environment for further testing and validation. 3. Identified and resolved bugs related to device document handling and completed testing in the development environment to ensure the workflow functions as expected. | N/A
7 | 09-10-2026 | 1. Completed the Client Device Registration document upload functionality, enabling direct document storage in MinIO during the registration process. 2. Completed end-to-end testing of the Client Device Registration document upload workflow in the development environment. 3. Identified and resolved bugs related to device document handling and performed regression testing in the development environment to ensure the workflow functions as expected. | N/A
8 | 12-10-2026 | 1. Identified and resolved bugs related to device document handling and performed regression testing in the development environment to ensure the workflow functions correctly and reliably. 2. Implemented document uploads directly from the Select Services page, eliminating the need to redirect users to the Device Details page. 3. Implemented document update functionality on the Select Services page, following the same workflow as the Device Details page. 4. Pushed the code to the development server and tested the document upload and update workflows on the Select Services page to verify that they function as expected. | N/A

## 349722
# | Date | Completed Today | Blockers
1 | 29-09-2026 | 1. Designed and created the required database tables and indexes for the Raise Ticket / Support Dashboard feature. 2. Structured the database to support Support Member management, service categories, support tickets, ticket assignment, ticket status tracking, document update requests, and related audit information. 3. Finalized the database structure based on the provided Support Dashboard Database Schema reference and prepared it for further implementation. | NA
2 | 30-09-2026 | 1. Started working on the Raise Ticket / Support Dashboard feature implementation and defining the overall workflow. 2. Working on the scalable implementation approach, including ticket creation, assignment, status tracking, support member management, and document update requests. 3. Reviewing the architecture and database integration to ensure the feature is **maintainable, scalable, and suitable for future enhancements. | NA
3 | 05-10-2026 | 1. Started working on the Raise Ticket / Support Dashboard frontend implementation based on the provided reference layout. 2. Working on integrating the Super Admin screens for Service Categories and Support Service Team, along with the Support Member dashboard and ticket management flow. 3. Reviewing the frontend architecture and existing authentication/role mechanism to ensure the implementation remains scalable and compatible with the existing Web Portal, without introducing a separate login or authentication system. | NA
4 | 06-10-2026 | 1. Continued working on the Raise Ticket / Support Dashboard frontend implementation based on the provided reference layout. 2. Continued implementation of the Super Admin screens for Service Categories and Support Service Team, along with the Support Member dashboard and ticket management flow. 3. Continued reviewing and refining the frontend architecture and existing authentication/role mechanism to ensure the implementation remains scalable and compatible with the existing Web Portal. | NA
5 | 07-10-2026 | 1. Continued working on the Raise Ticket / Support Dashboard frontend implementation and created a separate login page for Support Service Members. 2. Configured the Support Member login flow so that only users with the Support Service Member role can access it, preventing other roles from logging in through this page. 3. Added alerts and role-based restrictions to the main Web Portal login, clarifying that Support Service Members must use their dedicated login, while Client, Admin, Super Admin, and Tester users can continue using the main login. | NA
6 | 08-10-2026 | 1. Continued working on the Raise Ticket / Support Dashboard frontend implementation and the Support Service Member login flow. 2. Created a demo Support Service Member user to test and verify that the dedicated login functionality is working correctly with the required role-based access. 3. Continued testing the login restrictions and ensuring that only Support Service Members can access the dedicated login, while other roles are restricted from accessing it. | NA
7 | 09-10-2026 | 1. Prepared a PowerPoint presentation covering the end-to-end client onboarding and Functionality Sandbox workflow in the IoT Security Ecosystem & Sandbox Web Portal. 2. Documented the step-by-step process, including client login, Functionality Sandbox navigation, device selection/registration, test configuration, and test request submission. 3. Covered the C-DAC Bangalore workflow, test execution and status tracking, and generated test report availability in the client dashboard. | NA

## 350050
# | Date | Completed Today | Blockers
1 | 29-09-2026 | 1. Team Discussion regarding the Order Document Mapping & Version Resolution 2. Updated the doc & shared the team with respective Flow we finalised in meeting 3. Created initial DB Schema for the support dashboard & explained the team 4. Modification noted & required for device document mapping tables considering the ticket source by which Device doc has been updated | -
2 | 30-09-2026 | 1. Reviewed the backend implementation approach document for device document re-upload prepared by Thirumal. 2. Recommended including all predefined document categories in the JSON structure, even if no documents have been uploaded under a particular category, to maintain consistency across all orders. | -
3 | 05-10-2026 | 1. Researched the Security Sandbox. 2. Started designing the initial layout and content based on the discussions and insights shared during the event talks by Sam Sir. 3. Created a task for integrating the Support Dashboard with the Web Portal. | -
4 | 06-10-2026 | 1. Meeting with team to have a KT session to freshers for Git & Project Management Tool 2. Research on security sandbox | -
5 | 07-10-2026 | 1. Reserach On security sandbox 2. Meeting with aboli new team mate to have an overall picture of web portal for QA start 3. Attend the KT session from team with freshers | -
6 | 08-10-2026 | 1. Created the BUG EPIC and QA testing task. 2. Explained the bug reporting workflow to the QA team, including the process for raising, documenting, and sharing bugs. 3. Attended the Freshers session conducted by Aboli. 4. Followed up with the team to discuss task roadblocks and required resolutions. | -